## Sheet1
Project Name: School Name
Project Number: MPID #
ACTIVITY / MILESTONES |  |  | Forecast Date | Actual Date
Pre-Substantial Completion Requirements
Roof pre-final audit w/ punchlist
Final Roof Audit and Acceptance
HVAC Operational
Start up reports other equipment
Locksets re-keyed (TR/ER & Head End Rooms)
LAN & EMS
Proof-of-Performance (PoP) testing
Verification testing
Energy Mgmt. Systems (EMS) lines operational
Substantial Completion "SC" Process
| Pre-Closeout Conference |  | 2021-08-13
Substantial Completion Inspections by Architect, Engineers, and CCSD Maintenance
| Substantial Completion Certificate issued with punchlist |  | 2021-07-19
Temporary Certificiate of Occupancy "TCO"
Boiler inspection (State Fire Marshal & Travelers Insurance) w/ punchlist
Boiler tag by Travelers Insurance - Henry Parker
Final Documentation of 'decommissioned smoke fire dampers' approved by SFM and CCSD Bldg Official
Duct Cleaning Report
Critical life/safety NNC's cleared
State Fire Marshal Fire-Safety sign-off w. punch list (Sprinklers & Alarm)
Inspection Services sign-offs of electrical, mechanical, and plumbing final inspections, Life Safety sign-off
Certificate of Occupancy (C of O)
| All TCO Requirements complete |  | N/A
Punchlist Life/Safety items completed
| HVAC Balance Report (Approved) |  | Kent
| Final Commissioining Report (Approved) |  | Kent
| Final Sign-Off CCSD Inspection Permit Card (yellow card) |  | Brad
Systems Demonstration & Training
| Manufacturer training (during construction prior to On-Site training) |  | TBD
| On-Site Systems Demonstration and Training Event for (CCSD Maintenance) |  | 2021-09-03
FINAL ADMINISTRATIVE CLOSEOUT
| All Punch list items complete |  | 2021-08-31
| As built Drawings |  | 2021-09-02
| Record Documents ( Drawings, Project Manual, other) |  | 2021-09-02
Record Drawings
Record Specifications
| Spare Parts turnover (30 days prior to completion date) |  | 2021-08-18
O & M Manuals (approved by A/E / submit 3 wks prior to Sys Demo)
Warranties/Guarantees
Certificates of insurance for products and completed operations
Worker's Compensation certificate
Asbestos certificates
Contractor
Subcontractor
Unconditional and final releases
Consent of surety for release of final pay G706
Construction Keys Returned
| Labor Com Notice of Completion (Prior to FINAL Payment) |  | Kev
Final Pay Application submitted and approved.
Evaluations
| A/E |  | Team
Contractor
CCSD PM
Lessons Learned